## Timeline ProDoc
Outcome | Output # |  | Expected time to complete outputs
|  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
OC1 | OP1.1 | Regional in person kick-off capacity building workshop by ECLAC for 3 days and 20 participants involving statisticians and trade experts from seven beneficiary countries to raise awareness of the importance of trade in services statistics for policy and sharing of globally agreed methods, good practices and tools to compile high-quality, granular and timely trade in services statistics, including to measure gender equality and inclusiveness of trade | bar: Year 1 Q2
| OP1.2 | E-learning course developed and delivered to national statisticians and other experts of seven beneficiary countries, selected to reflect gender balance, with training to apply international standards, understand concepts, define data sources, set up or enforce collection systems, strengthen statistical processes, and disseminate high-quality statistics for policy. | bar: Year 1 Q3 to Year 2 Q1
| OP1.3 | Technical workshops/national training and advisory services provided in at least 4 target countries to define whether countries will benefit from using the TISSTAT system, install the system in beneficiary countries requesting it, or plan other enhancements, and test the improvements and ensure skills for their application as requested. | bar: Year 1 Q4 to Year 2 Q4
| OP1.4 | Statistical tools for development and analysis of trade in services adjusted and fit to the national conditions in at least 4 target countries. After having conducted a preliminary in-depth assessment of the status of trade in service data, including of data availability and quality, data collection practices, existing tools and data analysis processes, UNCTAD will guide selected countries in the (i) set up, (ii) pilot testing on a small sample of observations, (iii) deployment of TiSSTAT, or in the enhancement of existing survey tools to ensure trade in services statistics are properly collected, analyzed, and maintained following international standards and ensuring appropriate level of disaggregation, while mainstreaming gender- disaggregated data. Wherever feasible, the full survey will be designed and launched using TiSSTAT or enhanced existing survey tools. Survey design, including definition of the sampling frame, sampling algorithm, sample size, and survey target will be defined by the national statistical office, depending on the national context, statistical capacity, and financial and human resources availability, under UNCTAD technical guidance. ECLAC will provide local implementation and coordination support to such activities | bar: Year 2 Q3 to Year 3 Q4
OC 2 | OP2.1 | Report to analyze the role of services and services trade for strengthening resilience in the CARICOM region, including by using available data and statistics, sharing findings, good practice and examples in collecting and utilizing existing information, and providing policy advice to strengthen resilience and gender equality of services trade. | bar: Year 1 Q1 to Year 2 Q2
| OP2.2 | Advisory support to national trade policy makers for at least four target countries to analyze the services sector and services trade, national evidence needs and barriers to trade diversification and ensure benefits from the improved statistical capacity and processes, and the use of this evidence to identify focus areas for trade policy, including to address the specific challenges faced by these vulnerable groups of people in participating and benefitting from services trade. | bar: Year 1 Q4 to Year 3 Q2
| OP2.3 | Sub-regional workshop by ECLAC for 3 days and 20 participants involving trade experts and statisticians from seven beneficiary countries to share the progress, findings, and insights from country level work and to discuss further actions to address remaining challenges and identify synergies for collaboration and sub-regional action. | bar: Year 3 Q4 to Year 4 Q2

## 2025
OP | Activities | Notes | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.3 | Stering Committe meetings - quarterly | 3rd Meeting to be organized in January | bar: Jan; Apr; Jul; Oct
1.3 | Share the exploration environments | Should be ready for the online trainings | bar: Feb
1.3 | Share technical guides or other materials | TiSSTAT paper can be shared when published | bar: Feb to Mar
1.3 | Online workshop | The two-half-day virtual workshop will address any issues or questions identified during the testing phase: Day 1: Distribute the exploration environments and guides and cover any questions and problems Day 2: Focus on TiSSTAT modules and their functionality. | [12 empty] | Doodle form sent to statistical focal points (17-20 February) | bar: Feb
1.3 | Online trainings prior to the workshop | Regular monthly meetings as a follow up to the online training in February. UNCTAD support to countries. Idnetify countries requesting TiSSTAT installation for national data collection. | bar: Mar to Dec
1.4 | Technical workshop (in-person) | Technical workshops/national training and advisory services provided in at least 4 target countries to define whether countries will benefit from using the TISSTAT system, install the system in beneficiary countries requesting it, or plan other enhancements, and test the improvements and ensure skills for their application as requested. | Nov: End of November or December | End of November prefered