## Workplan
ID | Step | Activity | Involved (lead in bold) | Start date | End date | Tools
1 | Mapping of national agencies | Identify relevant national agencies and determine their roles: lead, supporting, other. Make a list of key stakeholders: the national focal point, representatives of lead agencies (experties and data), agency to carry out pilot calculations, supporting (methodological, infrastructural, administrative data and other support) agencies, and other authorities. | National consultant with support of National Focal point (UNCTAD support) |  |  | Guidelines, Part III, Chapter 2; Tool for mapping of national agencies
2 | Mapping of national agencies | Fill in the self-assessment questionnaire, reach out to key stakeholders for information. | National consultant with support of National Focal Point; (UNCTAD support) |  |  | Self-assessment questionnaire
3 | IFF risk assessment | Share research and studies, existing knowledge, information and estimates of IFFs and statistics on related topics like illegal economy, informal economy, non-observed economy etc., that you are aware of. | National consultant with support of National Focal Point with Statistical authorities; National stakeholders; (UNCTAD support) |  |  | Guidelines, Part III, Chapter 1; Self-assessment questionnaire, Part II, questions iv and v
4 | IFF risk assessment | Review, analyse and take stock of existing research, knowledge, information and estimates of IFFs and statistics on related topics like illegal economy, informal economy, non-observed economy etc. | National consultant jointly with National Focal Point (UNCTAD support)
5 | Meeting | Preliminary meeting to discuss self-assessment questionnaire, identify national stakeholders, determine details for the kick-off workshop, send out invitations. | National consultant, jointly with National Focal Point
6 | Meeting | Kick-off workshop 1. Introductions 2. Concept and methodologies for IFFs - UNCTAD, UNODC 3. Tour de Table by national agencies - work on IFFs to date - National Focal Point and stakeholders 4. Next steps for pilot testing | National consultant with National Focal Point with UNCTAD; National stakeholders |  |  | Reference materials: - Conceptual Framework - Measurement guidelines - Presentations
7 | Mapping of national agencies | Create a national IFF expert group - Technical Working Group (TWG) | National consultant with National Focal Point with National stakeholders; (UNCTAD support) |  |  | Model ToR for TWG
8 | IFF risk assessment | Interviews with experts to finalise the risk assessment with deeper insight on IFF risks and types of IFFs. | National consultant and National Focal Point; IFF expert group; National stakeholders (UNCTAD support) |  |  | Guidelines, Part III, Chapter 1
9 | IFF risk assessment | Analyse findings of the IFF risk assessment, identify gaps in statistics and statistical system to suggest short- and long-term priorities for statistical work. | National consultant with support of National Focal point (UNCTAD support)
10 | IFF risk assessment | Discuss and agree on short- and long-term priorities for statistical work on IFF statistics. | IFF expert group; Statistical authorities, National Focal Point; National stakeholders; (UNCTAD support) |  |  | Guidelines, Part III, Chapter 6
11 | Data availability review | Review available data held by different agencies, their quality and accessibility, and the legal frameworks affecting data and its use as well as the statistical capacity of involved agencies. | National consultant with support of National Focal point, Statistical authorities; IFF expert group; National stakeholders (UNCTAD support) |  |  | Tool for data availability and quality review
11 | Pilot testing plan | Based on types of IFF risks, available data and consultation with experts and stakeholder, suggest and prepare a draft definition of what is feasible to measure - operational definition. | National consultant with support of National Focal point; IFF expert group; (UNCTAD support)
12 | Pilot testing plan | Discuss, agree and adopt the operational definition. | IFF expert group; National Focal Point; National consultant (UNCTAD support) |  |  | Guidelines, Part III, Chapter 4
13 | Pilot testing plan | Prepare a draft pilot testing plan to propose selected method(s) and suggest a division of work between agencies to pilot test the measurement of selected IFFs, basing the decision on types of IFF risks and data availability. | IFF expert group; National Focal Point; National consultant (UNCTAD support)
14 | Pilot testing plan | Select method(s) and agree on a division of work between agencies to pilot test the measurement of selected IFFs, basing the decision on types of IFF risks and data availability. | IFF expert group; National Focal Point; National consultant (UNCTAD support) |  |  | Method evaluation framework, tier-classification of methods, and method fact sheets
15 | Training | Training workshop(s) on selected methodologies to launch pilot testing of measurement. | UNCTAD for IFF expert group; Statistical authorties; National stakeholders; National Focal Point; National consultant |  |  | Reference materials: - Conceptual Framework - Measurement guidelines - Presentations
16 | Measurement | Conduct measurement pilot testing and produce estimates of selected IFFs, and a report on the experience and lessons learned. | IFF expert group; National stakeholders; National consultant National Focal Point (UNCTAD support) |  |  | Pilot report template
17 | Action plan | Discuss the findings within the IFF expert group and other stakeholders and agree on an action plan with future improvement of data and statistics and goals to measure other types of IFFs. | IFF expert group; National Focal Point; National consultant National stakeholders; (UNCTAD support) |  |  | Action plan template